## GIS
Milestone/Activity | Start Date | End Date | Duration (Days) | Dependency/Input | Deliverable/Expected Output | Responsible Person/Team Contact | Status/Remark
Finalize EA boundaries | 2026-05-01 | 2026-06-15 | 45 | Satellite imagery | Boundary shapefiles | Wusu Kamara | Ongoing 60%
Produce enumeration maps | 2026-06-16 | 2026-09-30 | 106 | Boundary shapefiles | Printed EA maps | GIS Team | Not started
Missing name row test |  |  |  |  | no name provided |  | ongoing

## Publicity
Activity | Start | End | Days | Input | Output | Team Contact | Remarks
Launch media campaign | 2026-07-01 | 2026-07-20 | 20 | Approved budget | Media coverage report | ckoroma | Completed 100%
Print promotional materials | 2026-07-05 | 2026-13-40 | 10 | Design approval | Printed flyers | External Vendor | at risk